## Sheet1
F&L AI Projects — Timelines & Granular Break-up
Prepared for Chairman ¦ Reference Date: 4 May 2026 (business clarity baseline)
PROJECT 1 — Project Impetus (Cortex): Pivot to Category-Led & Autonomous Planning ¦ Plan & Buy modules
Assumption: All business clarity (hierarchy mapping, brand-allocation rules, pilot Hit/Year, etc.) achieved by 4 May 2026 (Day 0). Day 1 = 5 May 2026. 15 working days, Go/No-Go on Day 15 = 25 May 2026.
Module / Workstream | Step | Substep / Deliverable | Start | End | Status
Pre-work | Business Clarity & Decisions | Category × Subcategory hierarchy mapping; brand-allocation rules; minimum brand allocation threshold finalised in writing | — | 2026-05-04 | Pre-req
Pre-work | Pilot Hit/Year identified | Pilot Hit/Year and pilot store formats locked | — | 2026-05-04 | Pre-req
Week 1 — Foundation | Foundations | Master Category × Subcategory hierarchy created and populated; category-led AOP & planogram structures created; mapping completeness validated (every brick mapped) | 2026-05-05 | 2026-05-05 | Planned
Week 1 — Foundation | AOP Breakdown | Category-led AOP breakdown built; top-line splits by category in parallel with brand-led split | 2026-05-05 | 2026-05-06 | Planned
Week 1 — Foundation | OTB | OTB updated to run in category-led mode; data feeds (sales, stock, inward, forecast) rebuilt at new grain; per-approach config switches | 2026-05-06 | 2026-05-07 | Planned
Week 1 — Foundation | OTB Orchestration | OTB runs brand-led and category-led in parallel for the same Hit/Year | 2026-05-07 | 2026-05-07 | Planned
Week 1 — Foundation | Range Architecture | RA built brand-free at category × subcategory × brick × fashion grade; historical RA builder updated; approach & costing-submission status tracked per Hit/Year | 2026-05-07 | 2026-05-08 | Planned
Week 1 — Foundation | Brand Allocation Engine | Scoring logic, allocation rules, manual override path | 2026-05-08 | 2026-05-11 | Planned
Week 1 — Foundation | Plan Tagging | Brand-led and category-led plans clearly distinguished in the system | 2026-05-08 | 2026-05-08 | Planned
Week 1 — Foundation | Reconciliation | Cross-check: category-led AOP & OTB totals match brand-led totals at site × month (Eng + Business) | 2026-05-11 | 2026-05-11 | Planned
Week 1 — Foundation | Integration Testing | Integration tests across AOP, OTB, RA — both approaches | 2026-05-11 | 2026-05-11 | Planned
Week 2 — Experience & Downstream | OTB Dashboard | Approach toggle and dual-view (brand-led / category-led); approach filter across all OTB views | 2026-05-12 | 2026-05-12 | Planned
Week 2 — Experience & Downstream | Range Dashboard | Category-led navigation supported (category → subcategory → brick) | 2026-05-12 | 2026-05-13 | Planned
Week 2 — Experience & Downstream | Brand Allocation Review | Review panel inside Range Dashboard — buyers can see/accept/override system-assigned brand per category slot | 2026-05-13 | 2026-05-13 | Planned
Week 2 — Experience & Downstream | Planogram Uploader | Category-led planogram upload for VM / Space Planning | 2026-05-13 | 2026-05-14 | Planned
Week 2 — Experience & Downstream | Costing-System Submission | Submission flow with approach selection, lock-in warning, mutual-exclusion (one approach per Hit/Year) | 2026-05-14 | 2026-05-14 | Planned
Week 2 — Experience & Downstream | Admin & Navigation | Admin pages (approach per Hit/Year and per module); hierarchy navigator supports both trees | 2026-05-14 | 2026-05-14 | Planned
Week 2 — Experience & Downstream | Buy Plan | Buy Plan auto-detects committed approach; reads correct OTB & planogram; approach indicator in UI | 2026-05-14 | 2026-05-15 | Planned
Week 2 — Experience & Downstream | Distribution Plan | Reads correct planogram by approach; approach indicator in UI | 2026-05-15 | 2026-05-15 | Planned
Week 2 — Experience & Downstream | Mutual Exclusion | One-approach-per-Hit/Year rule enforced end-to-end | 2026-05-15 | 2026-05-15 | Planned
Week 2 — Experience & Downstream | Costing Integration | Integration with the costing system updated to handle either approach | 2026-05-15 | 2026-05-18 | Planned
Week 2 — Experience & Downstream | End-to-End Test | Full flow tested: Range Architecture → Costing → Buy Plan → Distribution Plan, both approaches | 2026-05-18 | 2026-05-18 | Planned
Week 3 — Test, Validate, Train | Comprehensive Testing | Testing across all modified modules | 2026-05-19 | 2026-05-19 | Planned
Week 3 — Test, Validate, Train | Integration Testing | Full end-to-end flow integration tests for both approaches | 2026-05-19 | 2026-05-20 | Planned
Week 3 — Test, Validate, Train | Reconciliation | Brand-led totals reconcile to category-led totals at site, month, category, brick, fashion grade | 2026-05-20 | 2026-05-20 | Planned
Week 3 — Test, Validate, Train | Performance | Both approaches running in parallel confirmed within SLA | 2026-05-20 | 2026-05-20 | Planned
Week 3 — Test, Validate, Train | Brand Allocation QA | Quality review of brand allocation with merchandising & brand managers (pilot data) | 2026-05-20 | 2026-05-21 | Planned
Week 3 — Test, Validate, Train | Regression | Edge-case and regression testing complete | 2026-05-21 | 2026-05-21 | Planned
Week 3 — Test, Validate, Train | UAT | User Acceptance Testing on pilot Hit/Year — buyers, planners, brand managers (business-led) | 2026-05-21 | 2026-05-22 | Planned
Week 3 — Test, Validate, Train | Training | User training on dual-view experience | 2026-05-22 | 2026-05-22 | Planned
Week 3 — Test, Validate, Train | Operations Walkthrough | Operations and VM team walkthrough | 2026-05-22 | 2026-05-25 | Planned
Week 3 — Test, Validate, Train | Readiness | Documentation, runbooks, rollback procedures finalised | 2026-05-25 | 2026-05-25 | Planned
Week 3 — Test, Validate, Train | Go / No-Go Decision | Pilot Hit/Year go-live decision (Business + Engineering) | 2026-05-25 | 2026-05-25 | Milestone
Post Go-Live | Pilot Hit/Year Execution | Run pilot Hit/Year fully category-led; brand-led continues for in-flight Hit/Years (coexistence) | 2026-05-26 | Ongoing | Planned
Post Go-Live | Broader Rollout | Migration Hit/Year-by-Hit/Year as each commits to category-led approach | Jun 2026 onwards | Phased | Planned
PROJECT 2 — AI Photoshoot: AI-Powered Catalogue Photoshoot Generation at Scale
Generates professional e-commerce catalogue images from flat-lay/mannequin shots. Modes: Instant, Batch, Single Image. Fully agentic — detection, auto-edit, scoring, delivery to GCS/CDN.
Module / Workstream | Step | Substep / Deliverable | Start | End | Status
Pipeline (10-step flow) | 01 — Upload | Product reference images (front/back/side) — clothing, footwear, lingerie | Live | Live | Live
Pipeline (10-step flow) | 02 — Analyse | Product views classified; garment details extracted (fabric, colour, pattern, silhouette) | Live | Live | Live
Pipeline (10-step flow) | 03 — Avatar & Pose | Avatar selection (gender, age, ethnicity); pose pool with 12 camera view types | Live | Live | Live
Pipeline (10-step flow) | 04 — Background & Lighting | Background image selection; lighting (direction, warmth, type) extracted for blending | Live | Live | Live
Pipeline (10-step flow) | 05 — Prompt | NL prompt assembled per pose: product + avatar + theme + view-aware lighting + filtered accessories | Live | Live | Live
Pipeline (10-step flow) | 06 — Generate | On-model images generated in parallel batches (up to 20 concurrent); 4K output | Live | Live | Live
Pipeline (10-step flow) | 07 — Detection | Unified Detection Agent — colour, logo, print, fabric, pose mismatches with code execution | Live | Live | Live
Pipeline (10-step flow) | 08 — Auto-Edit | Edit Agent surgical fixes via bounding boxes; validate-retry loop (max 2 attempts); identity & background preservation | Live | Live | Live
Pipeline (10-step flow) | 09 — Quality | Scored on 10.0 base; ≥7.0 → Approved; below routes to Manual QC. Auto QC currently 8.06/10 | Live | Live | Live
Pipeline (10-step flow) | 10 — Deliver | Final images to GCS, resolution-optimised, available via CDN; Ajio-standard naming | Live | Live | Live
Category Coverage | Men's Western — Shirts, T-shirts | Production-ready | Live | Live | Live
Category Coverage | Men's Western — Denim (Non-Washed) | Current focus; clean denims & solid washes work well | Live | Live | Live
Category Coverage | Men's Western — Denim (Washed/Distressed) | Active R&D — washed/distressed patterns difficult to replicate | Active R&D | Ongoing | Partial
Category Coverage | Men's Western — Non-Denim Bottoms | Production-ready | Live | Live | Live
Category Coverage | Women's Western — Tops, Dresses, Jackets | Production-ready | Live | Live | Live
Category Coverage | Women's Western — Bottoms | Production-ready | Live | Live | Live
Category Coverage | Women's Ethnic Wear — Kurtas, Sets | Under development — proper draping, embroidery, cultural authenticity | In Progress | 2026-05-28 | Upcoming
Category Coverage | Kids Apparel — Boys & Girls | Production-ready | Live | Live | Live
Category Coverage | Footwear — Men & Women | Shoe-specific prompt builder with ground contact | Live | Live | Live
Category Coverage | Lingerie / Innerwear | Conversation-thread approach, text-based model identity (NSFW workaround); samples for Red Tag | Live (New) | Live | Live
Category Coverage | Bags & Accessories | Pose pool available; expanding coverage | Partial | Ongoing | Partial
Execution Track Record | Trends Reboot — 4K Catalogue Digitization | 9,936 raw images → 2,975 styles, 3,957 products, 47,473 images generated (12 shots/product) — pushed to GCS for Ajio listing; pipeline V1→V2→V3 | Live | Delivered | Live
Execution Track Record | Lingerie Pipeline Unlocked | 8-stage pipeline (C1–C8); ZIP bulk processing; sample outputs for Red Tag | Live | Delivered | Live
What's Next | Ethnic Wear Pipeline | Initial capability — kurtas, kurta sets, ethnic dresses | In Progress | 2026-05-28 | Upcoming
What's Next | Washed Denim Improvement | Active R&D for washed/distressed denim patterns | In Progress | TBD (post-May) | Upcoming
What's Next | Pipeline Stitching | End-to-end automation: data curation → generation → optimisation → GCS upload | Live | Live | Live
What's Next | Segmentation Pipeline | Fabric swatch shot generation for PDP enhancement | In Progress | 2026-06-01 | Upcoming
What's Next | Auto-Edit at Scale | Expand auto-detection / auto-edit coverage across all categories | Ongoing | 2026-06-01 | Upcoming
What's Next | Accuracy Improvements | Continuous quality improvements with feedback from Ajio cataloguing & brand partners | Ongoing | Continuous | Live
PROJECT 3 — Project Impetus (AI Design Agent): Agentic AI for Production-Ready Garment Design
Multi-agent autonomous system: trend brief → garment images (front + back, on-model, 2K), artworks, swatch panels, BOM costing. Modes: Hybrid, Standard, Variation. Mapped against the 43 F&L category pods.
Module / Workstream | Step | Substep / Deliverable | Start | End | Status
Pipeline (8-step flow) | 01 — Brief Ingestion | Brand DNA, season direction, category specs, moodboard palette ingested from trend engine | Live | Live | Live
Pipeline (8-step flow) | 02 — Context Agent | Loads design brief; extracts brand palette, silhouette direction, prints, fabric preferences | Live | Live | Live
Pipeline (8-step flow) | 03 — Artwork Generation | 0–3 artwork images per garment with smart print detection; placement / AOP artworks; VLM quality review | Live | Live | Live
Pipeline (8-step flow) | 04 — Garment Image | Full garment image (front + back, on-model, 2K) with zone-aware artwork placement, gender-correct model | Live | Live | Live
Pipeline (8-step flow) | 05 — Quality Review | VLM reviewer scores 30+ checks; auto-retries on failure | Live | Live | Live
Pipeline (8-step flow) | 06 — BOM Costing | Cost per piece via costing API (fabric, trims, SMV, overheads) | Live | Live | Live
Pipeline (8-step flow) | 07 — Variation Engine | N silhouette/colour variations from reference images using moodboard palette — range building & style explosions | Live | Live | Live
Pipeline (8-step flow) | 08 — Delivery | Images uploaded via presigned URLs; per-style webhook callbacks fired in real-time | Live | Live | Live
Men's Apparel (Pods 1–9) | Pod 1 — Men Western: Denim Bottoms | Production-ready | Live | Live | Live
Men's Apparel (Pods 1–9) | Pod 2 — Men Western: Non-Denim Bottoms | Production-ready | Live | Live | Live
Men's Apparel (Pods 1–9) | Pod 3 — Men Western: Casual T-shirts | Production-ready | Live | Live | Live
Men's Apparel (Pods 1–9) | Pod 4 — Men Western: Casual Shirts | Production-ready | Live | Live | Live
Men's Apparel (Pods 1–9) | Pod 5 — Men Western: Formal Shirts | Production-ready | Live | Live | Live
Men's Apparel (Pods 1–9) | Pod 6 — Men Western: Formal Trouser & Suits | Production-ready | Live | Live | Live
Men's Apparel (Pods 1–9) | Pod 7 — Men Indian: Festive Wear | Live; sherwani craft-detail accuracy improvement targeted by 28–30 May 2026 | Live | 30 May 2026 (enh.) | Live
Men's Apparel (Pods 1–9) | Pod 8 — Men: Sports / Athleisure | Basic designs good; dynamic/complicated fabrics improvement | Partial | 2026-05-28 | Partial
Men's Apparel (Pods 1–9) | Pod 9 — Men: External Brands | 3P marketplace brands — N/A | N/A | N/A | Partial
Women's Apparel (Pods 10–18) | Pod 10 — Women: Western Tops | Production-ready | Live | Live | Live
Women's Apparel (Pods 10–18) | Pod 11 — Women: Western Dresses, Jackets, Blazers | Live; complex drape constructions enhancement | Live | 25 May 2026 (enh.) | Live
Women's Apparel (Pods 10–18) | Pod 12 — Women: Western Denim Bottoms | Production-ready | Live | Live | Live
Women's Apparel (Pods 10–18) | Pod 13 — Women: Western Non-Denim Bottoms | Production-ready | Live | Live | Live
Women's Apparel (Pods 10–18) | Pod 14 — Women Indian: Kurta / SKD / Bottoms | Production-ready | Live | Live | Live
Women's Apparel (Pods 10–18) | Pod 15 — Women Indian: Saree / Lehenga | Saree draping pipeline in development | Partial | 2026-05-30 | Partial
Women's Apparel (Pods 10–18) | Pod 16 — Women Indian/Fusion: Festive SKD | Production-ready | Live | Live | Live
Women's Apparel (Pods 10–18) | Pod 17 — Women: Sports / Athleisure | Basic designs good; dynamic/complicated fabrics improvement | Partial | 2026-05-28 | Partial
Women's Apparel (Pods 10–18) | Pod 18 — Women: External Brands | 3P marketplace brands — N/A | N/A | N/A | Partial
Kids Apparel (Pods 19–21) | Pod 19 — Kids: Infant | Production-ready | Live | Live | Live
Kids Apparel (Pods 19–21) | Pod 20 — Kids: Boys | Production-ready | Live | Live | Live
Kids Apparel (Pods 19–21) | Pod 21 — Kids: Girls | Production-ready | Live | Live | Live
Footwear & Accessories (22–28, 34) | Pods 22–25 — Footwear (Sports, Men, Women, External) | 3D footwear pipeline — scoping phase | Scoping | 30 May 2026 (scope) | Upcoming
Footwear & Accessories (22–28, 34) | Pod 26 — Innerwear: Men & Women | Basic styles covered; expanding to structured innerwear | Partial | 2026-05-25 | Partial
Footwear & Accessories (22–28, 34) | Pod 27 — Accessories: Gold & Jewellery | Requires accessories pipeline | Not yet | 2026-06-01 | Upcoming
Footwear & Accessories (22–28, 34) | Pod 28 — Accessories: Others (Bags, Belts, Wallets) | Requires accessories pipeline | Not yet | 2026-06-01 | Upcoming
Footwear & Accessories (22–28, 34) | Pod 34 — Beauty | Out of scope — separate division | Out of scope | Out of scope | Partial
Quick Fashion (Pods 29–33) | Pod 29 — Quick Fashion Women | Production-ready | Live | Live | Live
Quick Fashion (Pods 29–33) | Pod 30 — Quick Fashion Men | Production-ready | Live | Live | Live
Quick Fashion (Pods 29–33) | Pod 31 — Quick Fashion Kids | Production-ready | Live | Live | Live
Quick Fashion (Pods 29–33) | Pod 32 — Quick Fashion Footwear | Depends on footwear pipeline | Pending | 30 May 2026 (scope) | Upcoming
Quick Fashion (Pods 29–33) | Pod 33 — Quick Fashion Accessories | Depends on accessories pipeline | Pending | 2026-06-01 | Upcoming
Premium / BTL & Luxury (Pods 35–43) | Pod 35 — Premium Men | Variation Generator — buyers upload references; agent generates on-brand variations | Live | Live | Live
Premium / BTL & Luxury (Pods 35–43) | Pod 36 — Premium Women | Variation Generator — reference-based style explosions maintaining brand DNA | Live | Live | Live
Premium / BTL & Luxury (Pods 35–43) | Pod 37 — Premium Kids | Variation Generator — age-appropriate variations from reference images | Live | Live | Live
Premium / BTL & Luxury (Pods 35–43) | Pod 38 — L&BTL Men | Variation Generator — range building with Pantone-accurate colours | Live | Live | Live
Premium / BTL & Luxury (Pods 35–43) | Pod 39 — L&BTL Women | Variation Generator — range building with Pantone-accurate colours | Live | Live | Live
Premium / BTL & Luxury (Pods 35–43) | Pod 40 — Footwear & Accessories (Premium) | Requires separate pipeline | Not yet | 2026-06-01 | Upcoming
Premium / BTL & Luxury (Pods 35–43) | Pod 41 — Eyewear | Eyewear pipeline not yet scoped | Not yet | 2026-06-01 | Upcoming
Premium / BTL & Luxury (Pods 35–43) | Pod 42 — Indian Designer Wear | Lehengas, festive SKD covered; high-craft couture extending | Partial | 2026-05-30 | Partial
Premium / BTL & Luxury (Pods 35–43) | Pod 43 — Premium Home & Living | Home textiles pipeline not yet scoped | Not yet | TBD (post-Jun) | Upcoming
Execution Track Record | Trend Business — 718 Designs in <2 days | 10 brands (DNMX, Netplay, Team Spirit, Rio, Avaasa, Frendz, INF Frendz); ~60% avg selection rate | Live | Delivered | Live
Execution Track Record | Impetus × Superdry India — 20 Designs Live on Retail | SDX SS'26 capsule: 400+ designs in <10 days; 171 selected, 20 launched on Ajio | Live | Delivered | Live
What's Next — Improvements | Complex drape constructions — Dresses (Pod 11) & Structured Innerwear (Pod 26) | Improvement window | 2026-05-21 | 2026-05-25 | Upcoming
What's Next — Improvements | Dynamic athleisure fabric handling — Sports (Pods 8, 17) | Improvement window | 2026-05-25 | 2026-05-28 | Upcoming
What's Next — Improvements | Saree draping (Pod 15), high-craft Indian designer wear (Pod 42), sherwani craft details (Pod 7) | Improvement window | 2026-05-28 | 2026-05-30 | Upcoming
What's Next — Strategic | Variation Engine at Scale | Reference-based range building with Pantone-accurate moodboard colours | Live | Live | Live
What's Next — Strategic | Premium brands via Variations | Pods 35–39 served via Variation Generator — buyers upload references | Live | Live | Live
What's Next — Strategic | Trend-to-Design Closed Loop | Trend Agent outputs feed directly into Design Agent — fully autonomous brief-to-design | In Progress | 2026-06-01 | Upcoming
What's Next — Strategic | Delta Categories — Footwear, Accessories, Eyewear, Home | Category-specific pipelines; scoping underway | Scoping | 2026-06-01 | Upcoming
What's Next — Strategic | Eval-driven Improvement | Continuous automated VLM evaluation; weakest dimension (Brief adherence at 79) is the active target | Ongoing | Continuous | Live
STATUS LEGEND
Live | In production today
Partial | Live for some sub-segments / under active R&D
Upcoming | Scheduled — see End date
Pre-req | Business decision required before kickoff
Milestone | Key Go/No-Go gate
Planned | Scheduled inside the 3-week build window