## Sheet1
| Program Name: | ALP
| Initiative | Steps | Description | Status | Comments
1 | Governance & Access | 1. Development of Reliance SAML SSO authentication for logging. | Ensuring only RIL employees are able to login using their SSO | Done | Development was done
|  | 3. Role-based access contol (RBAC) implementation | Implementation of who can see, update and approave what in the platform across states and businesses | Done
4. Data gathering from all (or some) state and formats for access control (read/ edit/ approve) priviledges
|  | 5. Configuration of RBAC based on the above two and testing |  | Done
2 | Ingestion and usage of AOP & catchment data in ALP | 1. Upload AOP data in the desired format | This data and implementation is needed to start the journey of a lead in the system, ensure they automatically update the AOP status as the leads progress in their journey.
|  | 2. Implementation to use the data for dashboard funnel and cards |  | Done
3. Implementation to tag the catchment data for each lead that gets created
3 | ALP Dashboard | 1. AOP funnel in card format for both RE and BT team | The user facing view of the AOP funnel and leads table | Done
2. Table view of lead progression with filter and search functionality
4 | Lead Creation | 1. Detailed Lead generation form | The existing form would be incorporated here | Done
|  | 2. Lead ID Generation | A unique identifier that would be used to connect to all other tools via integration later
|  | 3. Ability to upload documents and add comments | This ensures exchange of emails is removed from existing process | Done
5 | Lead Journey and its workflow | 1. Lead details page with Status Progress and Activity timeline widgets | This is the rewamped digital journey of the lead starting from scouting till HOTO.
|  | 2. Ability to upload attachments, comments across stages and forms |  | Done
3. Ability to capture details of existing forms like SOW, site evaluation, etc. starting with only SOW in MVP
|  | 4. Approval mechanism by multiple functions |  | Done
5. Manual updates of key statuses happening in other portals such as R-Dash, Sirion, Board, SAP and FR portal. (These integrations will happen in phase two)
6 | Proto for feedback | 6. An early prototype without backend integration to get feedback from a limited set of users in RE, BT and NSO team | UAT for FE only | Done
7 | Business feasibility scoring by AI agent | 1. Ingestion of location intelligence summary fron Retail Vista | Leveraging AI to standardise and expedite decision making for giving a go-ahead for each site
|  | 2. Data gathering on criteria and definition of a good site from all (or some) business format |  | Out of scope
|  | 3. Using above two data points with existing data captured by RE and BT teams to arrive at a AI generated score and recommendation |  | Out of scope
8 | Email alerts and escalations | 1. Data gathering from all (or some) state and formats for email recipients, SLAs & escalation heirarchy. | A critical ask by NSO team that helps them monitor key bottlenecks and escalate when necessary | Done
2. Set up of 5-10 emails based on relevant triggers in the workflow
9 | Feedback and Testing | 1. Feedback incorporation from functions on Proto, PMs, and other team members |  | In Progress
|  | 2. Testing |  | In Progress
Risk Register
| Problem Statement | Description | Owner
1 | Technical dependency | The first implementation (SAML) may lead to some unknowns while following all guidelines of IRM
2 | Dependency on other tool | Dependency on Retail Vista for location intelligence that has to be used for business feasibility approval
3 | Dependency on data on task ownerships across functions | Dependency on different functions for data gathering so that RBAC, SLAs and Emails could be configured
4 | Dependency on time taken to collect feedback | We plan to share a prototype with dummy data by March mid. Quick feedback by all functions would help course correct if anything critical is missing
2nd Phase
| Dashboard |  | User level personalized alerts, and insights. Better leadership view.
| Lead Creation |  | Basic lead creation on mobile in offline mode.
| Approvals and Workflows |  | Advanced SLA and escalation matrix
| Business feasibility scoring by AI agent |  | Advanced Scoring Logic and Comparison Mode
| Integration |  | 1. With internal tools - Board, FR Portal 2. With external tools - R-Dash, Sirion, SAP
| Integration |  | 1.Retail Vista and HRMS integrations are mandatory (with fallback and employee data uploads), while all other system integrations will operate via manual update provisions.
1. Retail Vista finalises the catchments for each state and Businesses. 2.Auto-fetch Catchment ID via Retail Vista integration.
2. Data gathering from all state and formats for access control, SLAs & approval/escalation heirarchy.

## Sheet2
| Program Name: | ALP |  |  | Functional Owner: |  |  | Program Owner: | Other Key Members: | Irin Mathew
| Initiative | Steps | Description | Start Date | End Date | Owner | Status | Remarks
1 | Feedback on the previous version | Critical feedback points that are urgent should be added to the roadmap | Estimate will be based on the feedback and level of change expected
2 | Business feasibility scoring by AI agent | 1. Feedback collection on AI output |  |  |  |  | Not Started
2. Incorporate more attributes and with different weightages
|  | 3. Iterations on prompts, agent architecture to improve its output |  |  |  |  | Not Started
3 | Integrations | 1. Retail Vista for Catchment IDs and other relevant data |  |  |  |  | Not Started
2. Board - Re-direction and information exchange
3. FR Portal - Re-direction and information exchange
4. R-dash - Re-direction and information exchange
5. SAP - Re-direction and information exchange
|  | 6. Sirion - Re-direction and information exchange |  |  |  |  | Not Started
4 | Dashbaord | 1. User level pending action items | Pending action when a user signs in to the dashboard
|  | 2. Better insights for leadership team | More reports, better visualization
5 | Lead Creation | 1. Lead creation on Mobile with limited fields
2. Lead creation on Mobile in Offline Mode
3. Re-visit Lead ID logic based on Catchment ID from Retail Vista
6 | Approvals and wokrflows | 1. Advanced SLA and escalation matrix
7 | Advance forms incorporation | 1. Term Sheet
|  | 2. LDD |  |  |  |  | Not Started
3. Site Evaluation Report
4. Rent Intelligence Dashboard
5. License Tracking
6. Maintenance
Risk Register
| Problem Statement | Description | Owner | Resolution ETA
1 | Offline Mobile mode access | Technically there would be some workaround but it has to meet Reliance's info sec standards
2 | Scale of feedback on the previous version | If the feedback suggests a lot of changes, it will add to timeline
3 | AI output iterations | LLM output is always probalistic. For most products, it takes several iterations and testing by end users before it becomes valuable.
4 | Versions and iterations in these advanced forms | These forms are different versions and also go through changes. These also vary across business formats. As of Feb 19th, PM team needs to spend more time to gather more information and think of a good solution
5 | Integrations | The speed of execution depends a lot on API documentations, support from other tool owners, resolution of queries and testing by end users.
Not Started
Not Started
Not Started
Not Started
Not Started