## Forge Production Readiness
FYND FORGE — PRODUCTION READINESS CHECKLIST
NeoLync EMS — Fynd Forge MES Go-Live Validation
Version 2.0 ¦ 07-Apr-2026 ¦ AI-Native Manufacturing OS ¦ Phase 1: Planning & Traceability , Quality & Repair, Scan-Pack, ASN & Predictive Maintenance
SR # | Category | Checklist Item | Details / Acceptance Criteria (Forge-Specific) | Fynd Status | NeoLync Status | DRI (Owner) | DRI (Reviewer) | Target Date | Remarks / Evidence
1. PRODUCT MASTER & SKU CONFIGURATION IN FORGE
1 | Product Master | Finished Good (FG) SKUs created in Forge | All FG product SKUs created with correct item code, description, UoM, product category, and classification in Forge Product Master | Developed | Pending | Product Manager | NL MES Lead | 10th APRIL 2026
2 | Product Master | Semi-Finished Good (SFG) SKUs created | Sub-assembly / intermediate SKUs (PCBA, modules) created with parent-child hierarchy linkage in Forge | Developed | Pending | Product Manager | Engineering Lead | 10th APRIL 2026
3 | Product Master | Product attributes & specifications populated | Weight, dimensions, voltage, frequency, color, HW revision, FW version, certifications — all attributes filled in Forge product card | Developed | Pending | Product Manager | QA Lead | 10th APRIL 2026
4 | Product Master | Product images uploaded per SKU in Forge | High-res product images uploaded for visual identification at shop-floor stations; visible in Forge work instructions UI | Developed | Pending | Product Manager | NL MES Lead | 10th APRIL 2026
5 | Product Master | Product-wise customer mapping done | Each FG SKU mapped to customer / OEM brand for order-level traceability (Customer PO → FG SKU) | Developed | Pending | Product Manager | SCM Lead | 10th APRIL 2026
6 | Product Master | Product categorization (EMS product types) | Products categorized: IoT Devices, Routers, Set-Top Boxes, Smart Meters, PCBAs, Modules — per Neolync product portfolio | Developed | Pending | Product Manager | NL MES Lead | 10th APRIL 2026
2. MATERIAL MASTER & INVENTORY IN FORGE
7 | Material Master | All raw materials (RM) created in Forge | Every component: resistors, capacitors, ICs, connectors, PCB blanks — created with MPN, description, UoM, supplier AVL linkage | Developed | Pending | SCM Lead | NL MES Lead | 10th APRIL 2026
8 | Material Master | Consumables catalogued in Forge | Solder paste, solder wire, flux, adhesives, thermal compound, ESD packaging, cleaning agents — all created as consumable items | Developed | Pending | SCM Lead | Store Manager | 10th APRIL 2026
9 | Material Master | Packaging materials listed | Inner box, outer carton, foam inserts, poly bags, silica gel, bubble wrap, packing tape, labels — all as packaging item type | Developed | Pending | SCM Lead | Store Manager | 10th APRIL 2026
10 | Material Master | Approved Vendor List (AVL) linked per material | Each material has AVL with primary and alternate suppliers; supplier part numbers cross-referenced | Developed | Pending | SCM Lead | QA Lead | 10th APRIL 2026
11 | Material Master | Alternate / substitute components mapped | Approved alternate components (cross-reference parts) mapped in Forge for BOM flexibility during shortages | Developed | Pending | Engineering Lead | SCM Lead | 10th APRIL 2026
12 | Material Master | MSL (Moisture Sensitivity Level) configured | MSL levels (1-6) set for moisture-sensitive components; floor life tracking rules configured in Forge | Developed | Pending | QA Lead | Store Manager | 10th APRIL 2026
13 | Material Master | Shelf life & expiry tracking enabled | Date-code components, solder paste, adhesives — expiry alerts configured; FIFO enforcement rules active | Developed | Pending | QA Lead | Store Manager | 10th APRIL 2026
14 | Material Master | Opening inventory loaded in Forge | Physical stock audit completed; opening balances loaded in Forge; stock count matches physical count | Developed | Pending | Store Manager | Finance Lead | 10th APRIL 2026
15 | Material Master | Safety stock & reorder levels configured | Min/max stock levels, reorder points set per material for shortage alerting in Forge | Developed | Pending | SCM Lead | Production Planner | 10th APRIL 2026
16 | Material Master | Warehouse / bin locations configured in Forge | Storage locations (RM store, SFG store, FG store) and bin-level mapping set up for material movements | Developed | Pending | Store Manager | NL MES Lead | 10th APRIL 2026
3. BILL OF MATERIALS (BOM) IN FORGE
17 | BOM | Multi-level BOM created for all FG SKUs | FG → SFG (PCBA/module) → RM hierarchy uploaded in Forge BOM module; every level validated | Developed | Pending | Engineering Lead | NL MES Lead | 10th APRIL 2026
18 | BOM | BOM quantities per unit verified | Qty per assembly cross-checked against Gerber/design files; scrap allowance / wastage factor included | Developed | Pending | Engineering Lead | Process Engineer | 10th APRIL 2026
19 | BOM | BOM version control & revision history active | Active BOM version tagged; ECN (Engineering Change Notice) revision history maintained in Forge; old revisions archived | Developed | Pending | Engineering Lead | QA Lead | 10th APRIL 2026
20 | BOM | BOM change management (ECN) workflow configured | ECN workflow in Forge: Engineer raises change → QA reviews → Production acknowledges → Forge BOM updated with new revision | Developed | Pending | Engineering Lead | NL MES Lead | 10th APRIL 2026
21 | BOM | Phantom / reference BOM configured correctly | Non-stocked sub-assemblies (phantom BOMs) configured to auto-explode into work orders during production order creation | Developed | Pending | Engineering Lead | NL MES Lead | 10th APRIL 2026
22 | BOM | BOM vs physical kit reconciliation done | Trial kit prepared from store against BOM; every component physically verified; discrepancies resolved before go-live | Developed | Pending | Store Manager | Engineering Lead | 10th APRIL 2026
23 | BOM | Accessories BOM created separately | Power adapter, USB cable, user manual, warranty card, quick-start guide, packaging inserts — all in accessories BOM per FG | Developed | Pending | Product Manager | Store Manager | 10th APRIL 2026
24 | BOM | BOM cost roll-up validated with Finance | Standard material cost roll-up from RM → SFG → FG matches Finance expectations; cost sheet approved | Developed | Pending | Finance Lead | Engineering Lead | 10th APRIL 2026
25 | BOM | BOM cross-functional sign-off obtained | Engineering, Production, QA, SCM, Finance sign-off on final production BOM for each SKU in Forge | Developed | Pending | Engineering Lead | Plant Head | 10th APRIL 2026
4. ROUTING, STATIONS & WORK INSTRUCTIONS IN FORGE
4A. Site → Line → Station Hierarchy in Forge
26 | Plant Hierarchy | Site(s) created in Forge | Neolync plant site(s) created with address, timezone, working calendar; site-level KPIs configured | Developed | Pending | NL MES Lead | Plant Head | 10th APRIL 2026
27 | Plant Hierarchy | Production lines created under site | All SMT lines, assembly lines, testing lines, packing lines created under the site with unique line IDs | Developed | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
28 | Plant Hierarchy | Stations created under each line | Every work center / station configured: SMT Pick-n-Place, Reflow, Wave Solder, Manual Insert, Assembly, ICT, FCT, AOI, Labeling, Packing, OQC | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
29 | Plant Hierarchy | Station sequence / routing order defined | Station order set per product routing: e.g., Solder Paste Print → Pick & Place → Reflow → AOI → Manual Insert → Wave → ICT → FCT → Assembly → Packing | Developed | Pending | Process Engineer | Production Manager | 10th APRIL 2026
30 | Plant Hierarchy | Station-level KPIs configured in Forge | Target cycle time, throughput, FPY (First Pass Yield) targets set per station for real-time dashboard | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
4B. Routing & Operations
31 | Routing | Routing defined for every FG SKU in Forge | Complete station-by-station routing uploaded with operation name, sequence, work center, input/output materials | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
32 | Routing | Operation details per station documented | Each station has: operation type, required tools, required skills, input components from BOM, expected output | Developed | Pending | Process Engineer | QA Lead | 10th APRIL 2026
33 | Routing | Cycle time / standard time per station set | Target cycle time per station loaded for capacity planning, line balancing, and OEE calculation in Forge | Developed | Pending | Process Engineer | Production Planner | 10th APRIL 2026
34 | Routing | Mandatory scan points defined at each station | Forge mandatory scan enforcement: unit barcode scanned at station entry; interlock prevents skip; sequence enforced | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
35 | Routing | Component barcode binding configured | Critical components (PCB, enclosure, battery, display) barcode-bound to unit serial at designated stations | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
36 | Routing | Interlock / auto-routing rules configured | Forge interlocks: if any station fails → unit auto-routed to rework station; cannot proceed to next station until cleared | Developed | Pending | Process Engineer | QA Lead | 10th APRIL 2026
37 | Routing | Rework / rejection loop stations configured | Rework stations defined in routing; rework root-cause capture mandatory; re-inspection required before re-entering main line | Developed | Pending | QA Lead | Process Engineer | 10th APRIL 2026
38 | Routing | Routing change management process defined | Process for adding/removing stations, changing sequence, updating cycle times documented and workflow configured in Forge | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
4C. Work Instructions in Forge
39 | Work Instructions | Step-by-step work instructions uploaded per station | Visual work instructions with photos, diagrams, torque specs, orientation markers uploaded in Forge for every station | Developed | Pending | Process Engineer | QA Lead | 10th APRIL 2026
40 | Work Instructions | Work instruction images high-quality & clear | Close-up photos of component placement, screw locations, cable routing, label positions — clear enough for operator use | Developed | Pending | Process Engineer | Production Manager | 10th APRIL 2026
41 | Work Instructions | Work instruction version linked to BOM/routing revision | WI version tied to active BOM + routing revision; auto-prompt for WI update when BOM/routing changes via ECN | Developed | Pending | Process Engineer | Document Controller | 10th APRIL 2026
42 | Work Instructions | Work instructions visible on operator station UI | Operators can view current WI on their Forge station screen; step-by-step guidance during assembly/test | Developed | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
43 | Work Instructions | Quality checkpoints embedded in work instructions | In-process inspection steps, sampling criteria, pass/fail visual references included in WI per Forge quality module | Developed | Pending | QA Lead | Process Engineer | 10th APRIL 2026
5. PRODUCTION LINE INFRASTRUCTURE & MACHINE READINESS
5A. Machine & Equipment
44 | Machines | All machines registered in Forge | SMT (Pick & Place, Reflow, SPI), Wave Solder, AOI, X-Ray, ICT, FCT, Burn-in, Labeling, Packing machines — all tagged with asset ID in Forge | Developed | Pending | Maintenance Lead | NL MES Lead | 10th APRIL 2026
45 | Machines | Machine-to-station mapping done in Forge | Each physical machine mapped to correct Forge station / work center; machine ID linked | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
46 | Machines | Machine recipes / programs loaded per product | SMT placement programs, reflow solder profiles, AOI inspection recipes, SPI recipes, ICT/FCT test programs — per product SKU | Not Applicable | Pending | Process Engineer | Test Engineer | 10th APRIL 2026
47 | Machines | Changeover settings documented per product | Product changeover checklist: stencil change, feeder setup, program switch, torque settings — documented for controlled changeover in Forge | Developed | Pending | Process Engineer | Production Manager | 10th APRIL 2026
48 | Machines | Machine calibration certificates current | All machines calibrated with valid certificates; PM (Preventive Maintenance) schedule current; records available for audit | Developed | Pending | Maintenance Lead | QA Lead | 10th APRIL 2026
49 | Machines | Machine OEE baseline established | Baseline OEE (Availability × Performance × Quality) measured per machine; targets set in Forge dashboard | Developed | Pending | Process Engineer | Production Manager | 10th APRIL 2026
5B. Network & Internet Connectivity
50 | Network | LAN connectivity at every production station | Every workstation, scanner, label printer connected via Ethernet; speed ≥ 100 Mbps verified; cable labels applied | Not Applicable | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
51 | Network | Wi-Fi coverage validated on entire shop floor | Signal strength ≥ -65 dBm at all stations; dedicated SSID for Forge production systems; channel interference checked | Not Applicable | Pending | IT Lead | Network Engineer | 10th APRIL 2026
52 | Network | Internet uplink redundancy / failover tested | Primary ISP + secondary (backup ISP or 4G/5G failover) tested; automatic switchover verified; Forge remains accessible | Not Applicable | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
53 | Network | Firewall rules configured for Forge URLs | Forge On-Prem URLs (API, dashboard, edge endpoints) whitelisted; required ports opened; VPN configured if needed | Not Applicable | Pending | IT Security | IT Lead | 10th APRIL 2026
54 | Network | DNS resolution verified for Forge endpoints | All Forge URLs (app, API, websocket, edge sync) resolve correctly from every shop floor workstation | Not Applicable | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
55 | Network | Network latency & bandwidth tested under load | Concurrent Forge users + machine data streams tested; latency < 200ms to Forge On-Prem; no packet loss | Not Applicable | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
56 | Network | UPS / power backup for network equipment | Switches, routers, access points on UPS; production systems stay online during power fluctuations | Not Applicable | Pending | IT Lead | Maintenance Lead | 10th APRIL 2026
6. FORGE EDGE CLIENT & AUTOMATION TOOLS
6A. Edge Client Installation & Configuration
57 | Edge Client | Edge Client EXE installed on ALL line systems | Latest approved version of Forge Edge Client installed on every workstation / edge device across all production lines | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
58 | Edge Client | Edge Client version is latest approved release | Version number confirmed matching latest stable release; update/upgrade path documented (manual or auto-update) | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
59 | Edge Client | Edge Client pointing to PRODUCTION Forge URL | Each Edge Client instance configured to production environment URL (NOT staging / dev / UAT); environment verified | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
60 | Edge Client | Edge Client authentication / API keys configured | API keys, tokens, or certificates for Edge Client ↔ Forge On-Prem auth set up; JWT tokens rotating correctly | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
61 | Edge Client | Edge Client registered & visible in Forge dashboard | Each Edge Client shows as "online" with heartbeat in Forge dashboard; all lines/stations accounted for | Developed | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
6B. Machine Log Reading & File Paths
62 | Edge Client - Logs | Input file paths configured for SMT machine logs | Pick & Place, SPI, Reflow machine log directories (CSV/XML) mapped in Edge Client config; test with sample logs | Developed | Pending | IT Lead | Process Engineer | 10th APRIL 2026
63 | Edge Client - Logs | Input file paths configured for AOI / X-Ray logs | AOI inspection result files and X-Ray inspection logs directory paths set; defect image paths mapped | Developed | Pending | IT Lead | Process Engineer | 10th APRIL 2026
64 | Edge Client - Logs | Input file paths configured for ICT / FCT test logs | In-Circuit Test and Functional Test result file directories mapped; log format (CSV, XML, custom) confirmed | Developed | Pending | IT Lead | Test Engineer | 10th APRIL 2026
65 | Edge Client - Logs | Input file paths for burn-in / aging test logs | Burn-in rack monitoring log paths configured; temperature, duration, pass/fail data captured | Developed | Pending | IT Lead | Test Engineer | 10th APRIL 2026
66 | Edge Client - Logs | Output / write paths for processed data configured | Edge Client output directories for processed data, acknowledgements, and sync confirmations set | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
67 | Edge Client - Logs | Error log / diagnostic log paths configured | Edge Client own error logs, diagnostic logs, and audit trail paths set; log rotation configured | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
68 | Edge Client - Logs | Log parsing rules configured per machine type | Parser templates set for each machine vendor log format; field mapping (serial, result, measurements) validated with sample data | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
6C. Edge Client Data Sync & Reliability
69 | Edge Client - Sync | End-to-end data flow tested (Machine → Edge → Forge On-Prem) | Sample production data pushed from machine log → Edge Client parses → sends to Forge On-Prem → appears in Forge dashboard; verified | Developed | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
70 | Edge Client - Sync | Real-time data streaming validated | Machine data appears in Forge within defined SLA (< 5 seconds); no data lag under normal conditions | Developed | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
71 | Edge Client - Sync | Offline buffering / store-and-forward tested | Internet disconnected → Edge Client buffers data locally → internet restored → buffered data syncs to Forge without loss | Developed | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
72 | Edge Client - Sync | Retry logic on sync failure verified | Network timeout / API error → Edge Client retries with exponential backoff; no data duplication on retry | Developed | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
73 | Edge Client - Sync | Edge Client auto-start on system boot | Windows service / daemon configured to auto-start; recovery actions (restart on crash) configured | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
74 | Edge Client - Sync | Edge Client health monitoring & alerting | Heartbeat signal monitored; alert triggered if Edge Client goes offline > 5 min; escalation to IT Lead | Developed | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
75 | Edge Client - Sync | Edge Client update / upgrade plan documented | Process for rolling out Edge Client updates: staged rollout per line, rollback procedure, version compatibility matrix | Developed | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
6D. Automation Tools
76 | Automation Tools | Forge automation rules created for interlocks | Auto-routing rules: fail at AOI → route to rework; fail at ICT → hold for diagnosis; configured in Forge automation engine | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
77 | Automation Tools | Auto-capture from IIoT gateways configured | SPI, AOI, X-Ray, Reflow data auto-captured via IIoT gateway integration; no manual data entry for machine results | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
78 | Automation Tools | Automated SN/IMEI/MAC allocation scripts | Serial number generation, IMEI writing, MAC address allocation automation configured and tested in Forge | Developed | Pending | NL MES Lead | Test Engineer | 10th APRIL 2026
79 | Automation Tools | Automated label printing triggers configured | Barcode/QR label auto-prints at designated station upon scan; label template matched to product SKU; printer integration tested | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
80 | Automation Tools | Alert / notification rules configured | Forge alerts set for: FPY drop below threshold, machine downtime, sync failure, inventory shortage, interlock triggers | Developed | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
7. SERIALIZATION, IDENTIFIERS & UNIT-LEVEL TRACEABILITY
81 | Serialization | SN (Serial Number) generation scheme configured in Forge | Unique SN format: prefix (product/customer code) + date code + sequence + check digit; auto-generation rules set in Forge | Developed | Pending | NL MES Lead | Engineering Lead | 10th APRIL 2026
82 | Serialization | IMEI generation & writing configured (if applicable) | IMEI allocation pool loaded; IMEI writing station defined in routing; post-write verification step enforced | Developed | Pending | NL MES Lead | Test Engineer | 10th APRIL 2026
83 | Serialization | RSN (Return Serial Number) generation configured | RSN format and generation rules for RMA / warranty returns configured in Forge per product category | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
84 | Identifiers | Wi-Fi MAC address capture station & validation | Station in routing where Wi-Fi MAC is read from device; MAC format validated (XX:XX:XX:XX:XX:XX); stored in Forge unit record | Developed | Pending | NL MES Lead | Test Engineer | 10th APRIL 2026
85 | Identifiers | Bluetooth MAC address capture station & validation | BT MAC capture, format validation, uniqueness check against Forge database; reject if duplicate | Developed | Pending | NL MES Lead | Test Engineer | 10th APRIL 2026
86 | Identifiers | Ethernet MAC address capture (if applicable) | LAN MAC read at test station; stored in unit record; uniqueness validated | Developed | Pending | NL MES Lead | Test Engineer | 10th APRIL 2026
87 | Identifiers | Custom identifiers captured (HW rev, FW ver, model code) | Hardware revision, firmware version, model number, lot code — all captured at designated stations and linked to unit | Developed | Pending | NL MES Lead | Engineering Lead | 10th APRIL 2026
88 | Label Verification | Barcode / QR code label template created per product | Label templates in Forge: product label, serial label, compliance label, carton label — per SKU; correct data fields mapped | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
89 | Label Verification | Label verification scan configured | Post-print label scanned and verified against Forge data; mismatch triggers reject/alert per Forge label verification module | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
90 | Label Verification | Label printer integration tested | Zebra / TSC / other label printers integrated with Forge; test prints validated for readability & data accuracy | Developed | Pending | IT Lead | Process Engineer | 10th APRIL 2026
91 | Traceability | Binding / comparison rules configured in Forge | Component binding rules: e.g., PCB SN bound to device SN; MAC bound to IMEI; carton bound to device list — all configured | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
92 | Traceability | Complete genealogy chain validated end-to-end | Component lot → PCB SN → Device SN/IMEI → MAC addresses → Test results → Carton → Shipment — full chain traceable in Forge | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
93 | Traceability | Duplicate identifier detection & rejection active | Duplicate SN, MAC, IMEI detection enabled in Forge; hard stop / interlock prevents duplicate units from proceeding | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
94 | Traceability | Zero-gap audit trail verified | No gaps in unit history: every scan, test, rework, station pass is logged with timestamp, operator, station in Forge | Developed | Pending | NL MES Lead | Compliance Officer | 10th APRIL 2026
8. ASSEMBLY, ACCESSORIES & PACKING CONFIGURATION
8A. Assembly Readiness
95 | Assembly | Assembly kit list matches BOM in Forge | Kit list generated from Forge BOM; every component (PCB, enclosure, screws, cables, connectors, gaskets, thermal pads) verified | Developed | Pending | Production Planner | Store Manager | 10th APRIL 2026
96 | Assembly | Assembly jigs, fixtures & tooling available | All jigs, fixtures, torque drivers, press-fit tools, soldering stations available and calibrated per station | Developed | Pending | Maintenance Lead | Process Engineer | 10th APRIL 2026
97 | Assembly | Cosmetic inspection criteria with golden samples | Accept/reject criteria for scratches, dents, gaps, label alignment — golden sample photos uploaded in Forge work instructions | Developed | Pending | QA Lead | Process Engineer | 10th APRIL 2026
8B. Packing Configuration in Forge
98 | Packing Config | Packing station(s) defined in Forge routing | Packing station created with scan-pack workflow: unit scan → accessory scan → box scan → carton scan → seal | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
99 | Packing Config | Scan-Pack workflow configured per product | Forge scan-pack sequence: scan device SN → verify test pass → scan each accessory barcode → scan inner box → scan master carton | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
100 | Packing Config | Packing BOM / accessories checklist in Forge | Packing BOM per SKU: device + power adapter + USB cable + manual + warranty card + quick-start guide + packaging inserts — all items validated by scan | Developed | Pending | NL MES Lead | Product Manager | 10th APRIL 2026
101 | Packing Config | Inner box packing rules configured | Units per inner box, orientation, padding material, label position — rules set in Forge per SKU | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
102 | Packing Config | Master carton packing rules configured | Inner boxes per master carton, stacking pattern, max weight, carton label auto-print — configured in Forge | Developed | Pending | NL MES Lead | Logistics Lead | 10th APRIL 2026
103 | Packing Config | Packing label templates configured | Product label, inner box label, master carton label, shipping label — all templates created in Forge with correct data fields | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
104 | Packing Config | Packing weight / dimension validation | Expected weight range per packed unit configured; weight check at packing station; reject if out of tolerance | Developed | Pending | Process Engineer | QA Lead | 10th APRIL 2026
105 | Packing Config | Scan-pack error prevention rules active | Forge prevents: wrong accessory for product, duplicate unit in carton, missing accessory, wrong box size — all interlock rules | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
106 | Packing Config | Customer-specific packing requirements loaded | OEM/customer-specific packing instructions, label requirements, special inserts — configured per customer in Forge | Developed | Pending | Product Manager | NL MES Lead | 10th APRIL 2026
9. SHIFT CONFIGURATION & PRODUCTION SCHEDULING
107 | Shift Config | Shift definitions created in Forge | All shifts defined: Shift A (6AM-2PM), Shift B (2PM-10PM), Shift C (10PM-6AM) — or as per Neolync schedule; break times included | Developed | Pending | HR Lead / Production Manager | NL MES Lead | 10th APRIL 2026
108 | Shift Config | Shift calendar / working calendar configured | Working days, holidays, planned shutdown days configured in Forge calendar; affects capacity planning & OEE calculation | Developed | Pending | Production Manager | NL MES Lead | 10th APRIL 2026
109 | Shift Config | Shift-wise operator assignment configured | Operators assigned to shifts and lines/stations in Forge; shift-wise login enforced; attendance tracking active | Developed | Pending | Production Manager | NL MES Lead | 10th APRIL 2026
110 | Shift Config | Shift handover process defined in Forge | Shift handover checklist: pending units, machine status, quality alerts, rework queue — documented and viewable in Forge | Developed | Pending | Production Manager | NL MES Lead | 10th APRIL 2026
111 | Shift Config | Shift-wise production targets set | Daily/shift-wise production targets loaded per line per product; Forge dashboard shows target vs actual in real-time | Developed | Pending | Production Planner | Production Manager | 10th APRIL 2026
112 | Shift Config | Shift-wise OEE & downtime tracking active | OEE calculated per shift per line in Forge; downtime reasons captured (planned/unplanned) with codes | Developed | Pending | Process Engineer | NL MES Lead | 10th APRIL 2026
113 | Shift Config | Shift changeover downtime tracked | Time between shifts (changeover, cleaning, setup) tracked in Forge; impacts availability calculation | Developed | Pending | Process Engineer | Production Manager | 10th APRIL 2026
10. TESTING, QUALITY & INSPECTION IN FORGE
10A. Pre-Assembly / PCBA Testing
114 | Testing - SPI | SPI (Solder Paste Inspection) data auto-captured | SPI machine results streaming to Forge via Edge Client / IIoT gateway; volume, area, height data per pad captured | Developed | Pending | Test Engineer | NL MES Lead | 10th APRIL 2026
115 | Testing - AOI | AOI recipe loaded & defect library updated | AOI recipe trained on golden board per product; defect categories (missing, shifted, tombstone, bridge, polarity) configured in Forge | Developed | Pending | Test Engineer | Process Engineer | 10th APRIL 2026
116 | Testing - AOI | AOI results auto-captured in Forge | Pass/fail results + defect images flowing from AOI → Edge Client → Forge in real-time; AI inspection analytics available | Developed | Pending | Test Engineer | NL MES Lead | 10th APRIL 2026
117 | Testing - ICT | ICT program loaded & validated per product | In-Circuit Test fixtures ready; test program matches BOM revision; opens, shorts, component value limits configured | Developed | Pending | Test Engineer | QA Lead | 10th APRIL 2026
118 | Testing - ICT | ICT results logging to Forge configured | ICT pass/fail + individual measurement values flowing to Forge unit record via Edge Client | Developed | Pending | Test Engineer | NL MES Lead | 10th APRIL 2026
119 | Testing - FCT | FCT program loaded & validated per product | Functional Test scripts covering all product specifications: power, I/O, communication, sensors, display, audio | Developed | Pending | Test Engineer | QA Lead | 10th APRIL 2026
120 | Testing - FCT | FCT results logging to Forge configured | FCT detailed results (each test case pass/fail + measured values) flowing to Forge unit record | Developed | Pending | Test Engineer | NL MES Lead | 10th APRIL 2026
121 | Testing - FW | Test firmware / exe available & version-controlled | Test firmware and production firmware staged; version tracking in Forge; flashing station configured | Developed | Pending | Software Lead | Test Engineer | 10th APRIL 2026
10B. Post-Assembly / FATP Testing
122 | FATP | Final Assembly Test (FATP) program ready | Full product test post-assembly: power on, boot, connectivity (Wi-Fi/BT/LAN), UI, camera, sensors, peripherals | Developed | Pending | Test Engineer | QA Lead | 10th APRIL 2026
123 | FATP | FATP results auto-captured in Forge | FATP pass/fail + detailed measurements flowing to Forge via Edge Client or API; auto-interlock on fail | Developed | Pending | Test Engineer | NL MES Lead | 10th APRIL 2026
124 | FATP | Wi-Fi / BT RF test configured | RF test: TX power, RX sensitivity, signal strength, pairing test — limits set per spec; results to Forge | Developed | Pending | Test Engineer | QA Lead | 10th APRIL 2026
125 | FATP | Burn-in / aging test setup configured in Forge | Burn-in duration, temperature, power cycling defined; monitoring logs streamed to Forge; fail detection active | Developed | Pending | Test Engineer | QA Lead | 10th APRIL 2026
126 | FATP | Production firmware flashing & verification | Production FW flashing station in routing; post-flash version verification; FW version recorded in Forge unit record | Developed | Pending | Test Engineer | Test Engineer | 10th APRIL 2026
127 | FATP | Device provisioning & cloud registration | Device registers on customer cloud platform; credentials/certificates written; activation verified; record in Forge | Developed | Pending | Test Engineer | NL MES Lead | 10th APRIL 2026
128 | FATP | Safety testing (Hi-Pot, ground continuity) | Hi-Pot, ground continuity, leakage current tests per safety standards (IEC, UL); results logged to Forge | Developed | Pending | Test Engineer | Compliance Officer | 10th APRIL 2026
10C. Quality Management in Forge
129 | Quality | OQC (Outgoing Quality Control) sampling plan configured | AQL sampling plan defined per product in Forge; OQC station in routing; OQC checklist with pass/fail criteria | Developed | Pending | QA Lead | QA Manager | 10th APRIL 2026
130 | Quality | FPY (First Pass Yield) monitoring & alerts active | FPY calculated per station per product in real-time; Forge alert triggers if FPY drops below threshold (e.g., < 95%) | Developed | Pending | QA Lead | NL MES Lead | 10th APRIL 2026
131 | Quality | Defect capture with root-cause traceability | Defect logged with: defect type, station, operator, component lot, timestamp; root-cause traceable in Forge genealogy | Developed | Pending | QA Lead | NL MES Lead | 10th APRIL 2026
132 | Quality | MRB (Material Review Board) tracking configured | Quarantined / rejected units tracked in Forge MRB queue; disposition (rework, scrap, return to vendor) workflow active | Developed | Pending | QA Lead | Engineering Lead | 10th APRIL 2026
133 | Quality | Rework mandatory re-inspection enforced | Post-rework: unit must pass re-inspection at same station before re-entering main line; Forge interlock enforced | Developed | Pending | QA Lead | NL MES Lead | 10th APRIL 2026
134 | Quality | SPC (Statistical Process Control) monitoring active | Key process parameters (solder paste volume, reflow profile, test measurements) monitored with control charts in Forge | Developed | Pending | QA Lead | Process Engineer | 10th APRIL 2026
11. ORDER MANAGEMENT, INVOICING & DOCUMENTATION
135 | Orders | Customer PO received & linked in system | Customer Purchase Order captured in SAP/Forge with PO number, SKU, qty, delivery date, special instructions | Developed | Pending | SCM Lead | Production Planner | 10th APRIL 2026
136 | Orders | Sales Order created against Customer PO | Sales Order linked to Customer PO; correct pricing, payment terms, delivery schedule populated | Developed | Pending | SCM Lead | Finance Lead | 10th APRIL 2026
137 | Orders | Production Order created from Sales Order | Production Order generated with: product SKU, BOM revision, routing, qty, priority, target start/end date | Developed | Pending | Production Planner | NL MES Lead | 10th APRIL 2026
138 | Orders | Work Order(s) created in Forge from Production Order | Work Orders generated in Forge; linked to correct BOM, routing, line assignment; WO visible on shop floor | Developed | Pending | Production Planner | NL MES Lead | 10th APRIL 2026
139 | Orders | Purchase Orders raised for RM procurement | POs raised per BOM requirement against production plan; PO numbers in SAP; delivery tracking active | Developed | Pending | SCM Lead | Finance Lead | 10th APRIL 2026
140 | Orders | Material pick list / kit issue from store | Kit issue against WO from Forge; pick list auto-generated from BOM; shortage highlighted; material reserved | Developed | Pending | Store Manager | Production Planner | 10th APRIL 2026
141 | Orders | Invoice creation workflow tested | FG dispatch → invoice generation → tax calculation (GST) → e-invoice → customer delivery — full flow tested | Developed | Pending | Finance Lead | SCM Lead | 10th APRIL 2026
142 | Orders | Delivery challan & packing list generation | Auto-generated from Forge: packing list (serial-wise), delivery challan, shipping labels, AWB | Developed | Pending | Logistics Lead | Finance Lead | 10th APRIL 2026
143 | Orders | Customer PO → FG dispatch full traceability | End-to-end: Customer PO → SO → Production Order → WO → Unit SN → Test Results → Packing → Dispatch → Invoice — all traceable | Developed | Pending | NL MES Lead | Plant Head | 10th APRIL 2026
12. SHIPPING, ASN (ADVANCE SHIPPING NOTICE) & DISPATCH
144 | Shipping | FG warehouse / storage locations configured | FG store locations, bin mapping, rack assignments set in Forge/SAP for finished goods inventory | Developed | Pending | Store Manager | SCM Lead | 10th APRIL 2026
145 | Shipping | FG inward (production → FG store) workflow active | Packed units move from packing station → FG store; qty and serial validated in Forge; stock updated | Developed | Pending | Store Manager | Production Manager | 10th APRIL 2026
146 | Shipping | ASN (Advance Shipping Notice) generation configured | Forge generates ASN with: shipment details, carton list, serial numbers, carrier info — sent to customer electronically | Developed | Pending | NL MES Lead | Logistics Lead | 10th APRIL 2026
147 | Shipping | Shipment packaging validation before dispatch | Final scan at dispatch: every carton scanned, weight validated, label verified — Forge prevents wrong shipment | Developed | Pending | Logistics Lead | QA Lead | 10th APRIL 2026
148 | Shipping | Serial / MAC traceability at dispatch | Every shipped unit traceable by SN, MAC, IMEI in Forge for warranty claims, RMA, and customer support | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
149 | Shipping | DOA (Dead on Arrival) tracking loop | Customer DOA report → Forge RMA workflow → unit history pulled → root-cause analysis → corrective action | Developed | Pending | QA Lead | NL MES Lead | 10th APRIL 2026
13. FORGE DASHBOARDS, ANALYTICS & KPI REPORTING
150 | Dashboards | Real-time WIP (Work In Progress) dashboard active | Live WIP count per station, per line, per product visible in Forge dashboard; bottleneck alerts configured | Developed | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
151 | Dashboards | OEE dashboard configured per line / machine | OEE (Availability × Performance × Quality) calculated and displayed per line, per shift in Forge | Developed | Pending | NL MES Lead | Process Engineer | 10th APRIL 2026
152 | Dashboards | FPY dashboard with drill-down by station | First Pass Yield trend per station, per product; drill-down to defect pareto and root-cause analysis | Developed | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
153 | Dashboards | MTBF / MTTR maintenance dashboards active | Mean Time Between Failures and Mean Time To Repair tracked per machine in Forge; maintenance alerts configured | Developed | Pending | NL MES Lead | Maintenance Lead | 10th APRIL 2026
154 | Dashboards | Downtime tracking dashboard active | Downtime reasons (planned/unplanned), duration, frequency tracked per line per shift; Pareto analysis available | Developed | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
155 | Dashboards | Production target vs actual dashboard | Shift-wise, daily, weekly production target vs actual output visible; variance highlighted in Forge dashboard | Developed | Pending | NL MES Lead | Production Planner | 10th APRIL 2026
156 | Dashboards | Shortage / late order alerts configured | Forge proactive alerts for: material shortages impacting production, orders at risk of missing delivery date | Developed | Pending | NL MES Lead | SCM Lead | 10th APRIL 2026
14. USER ACCESS, RBAC & OPERATOR TRAINING
157 | Users & RBAC | All user accounts created in Forge | Every operator, supervisor, engineer, manager, QA, store, admin — login credentials created in Forge | Developed | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
158 | Users & RBAC | Role-Based Access Control (RBAC) configured | Roles: Operator, Line Supervisor, QA Inspector, Engineer, Store Manager, Production Manager, Plant Admin — permissions set per role | Developed | Pending | NL MES Lead | IT Security | 10th APRIL 2026
159 | Users & RBAC | Station-level access restrictions active | Operators can only access stations they are trained/certified for; Forge enforces per RBAC rules | Developed | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
160 | Users & RBAC | Operator login / badge scan at stations configured | Operator ID scan at station login; tracked in Forge for: who produced which unit at which station | Developed | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
161 | Training | Operator training on Forge station UI completed | Hands-on training: unit scan, component scan, defect logging, work instruction viewing, rework handling on Forge UI | Not Applicable | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
162 | Training | Supervisor training on Forge dashboards & WO management | Supervisor training: WO release, line monitoring, shift management, production reports, escalation in Forge | Not Applicable | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
163 | Training | QA team training on Forge quality module | QA training: OQC process, defect capture, FPY monitoring, MRB workflow, SPC charts in Forge | Not Applicable | Pending | NL MES Lead | QA Manager | 10th APRIL 2026
164 | Training | IT team training on Edge Client administration | IT team can: install, configure, troubleshoot, update Edge Client; monitor health in Forge dashboard; handle sync issues | Not Applicable | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
165 | Training | Training records & certification documented | Training attendance, skill matrix, station certifications maintained; Forge restricts access until certified | Not Applicable | Pending | HR Lead | NL MES Lead | 10th APRIL 2026
15. GO-LIVE VALIDATION, DRY RUN & HYPERCARE
166 | Go-Live | End-to-end dry run completed on Forge | Full cycle: WO creation → material issue → SMT → AOI → ICT → FCT → Assembly → FATP → Packing → Dispatch — all on Forge | Not Applicable | Pending | NL MES Lead | Plant Head | 10th APRIL 2026
167 | Go-Live | Dry run data integrity validated | All serial numbers, MAC addresses, test data, inventory movements, traceability chain verified post dry run in Forge | Not Applicable | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
168 | Go-Live | Edge Client data flow validated during dry run | Machine logs → Edge Client → Forge On-Prem — data integrity, completeness, and timeliness verified during dry run | Not Applicable | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
169 | Go-Live | Packing / scan-pack workflow validated during dry run | Full scan-pack cycle tested: device scan, accessory scan, box scan, carton scan, label print, weight check — all validated | Not Applicable | Pending | Process Engineer | QA Lead | 10th APRIL 2026
170 | Go-Live | Performance / load test under peak conditions | Concurrent operators on all lines + machine data streams + API sync — system response time < 2 sec; no timeouts | Not Applicable | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
171 | Go-Live | Backup & disaster recovery plan tested | Forge On-Prem backup schedule confirmed; restore tested; Edge Client local buffer tested; RTO/RPO documented | Not Applicable | Pending | IT Lead | NL MES Lead | 10th APRIL 2026
172 | Go-Live | Rollback plan documented & approved | Fallback to manual/previous system if Forge fails during go-live; rollback triggers, steps, DRIs documented | Not Applicable | Pending | NL MES Lead | Plant Head | 10th APRIL 2026
173 | Go-Live | Escalation matrix with L1/L2/L3 contacts | L1: Neolync IT; L2: Forge implementation team; L3: Fynd Forge engineering — contacts, SLAs, channels defined | Not Applicable | Pending | NL MES Lead | IT Lead | 10th APRIL 2026
174 | Go-Live | Go/No-Go sign-off from all department heads | Written approval: Production, QA, Engineering, IT, SCM, Finance, HR — all sign off on Forge production readiness | Not Applicable | Pending | NL MES Lead | Plant Head | 10th APRIL 2026
175 | Go-Live | Hypercare support plan (Week 1-4 post go-live) | On-site Forge support team for Week 1-2; remote support Week 3-4; daily sync calls; issue tracker active | Not Applicable | Pending | NL MES Lead | Fynd Support | 10th APRIL 2026
176 | Go-Live | Known issues & workaround register published | All known issues documented with: severity, workaround steps, target fix date, DRI; accessible to all stakeholders | Not Applicable | Pending | NL MES Lead | QA Lead | 10th APRIL 2026
177 | Go-Live | Forge SOP & quick-reference guides at every station | Laminated quick-ref cards at operator stations; digital SOP accessible in Forge; supervisor desk SOP binder ready | Not Applicable | Pending | NL MES Lead | Production Manager | 10th APRIL 2026
178 | Go-Live | Predictive maintenance baseline data loaded (Phase 3) | Machine performance baseline data loaded in Forge for future predictive maintenance activation per Phase 3 roadmap | Not Applicable | Pending | Maintenance Lead | NL MES Lead | 10th APRIL 2026

## Legend & Instructions
LEGEND & INSTRUCTIONS
Status Values
Pending | Not started or not validated
In Progress | Currently being worked on
Done | Completed and verified
Blocked | Cannot proceed; dependency or issue
N/A | Not applicable for this product/line
Forge-Specific Terminology
Forge | Fynd Forge — AI-native end-to-end electronics manufacturing OS
Edge Client | Forge Edge Client EXE — installed on shop floor systems to read machine logs and sync data to Forge On-Prem
Scan-Pack | Forge packing workflow: scan device → scan accessories → scan box → seal → label
Interlock | Forge enforcement rule: prevents unit from proceeding if previous station failed
Binding | Linking two identifiers together (e.g., PCB SN bound to device SN, MAC bound to IMEI)
Genealogy | Complete unit traceability: component lot → PCB → device → test → carton → shipment
FPY | First Pass Yield — % of units passing a station on first attempt
OEE | Overall Equipment Effectiveness = Availability × Performance × Quality
FATP | Final Assembly, Test & Pack — post-assembly testing phase
ASN | Advance Shipping Notice — electronic notification to customer before shipment arrives
MRB | Material Review Board — disposition process for non-conforming units
SPC | Statistical Process Control — monitoring process parameters with control charts
IIoT Gateway | Industrial IoT gateway connecting SPI, AOI, X-Ray, Reflow machines to Forge
Phase 1 | Planning & Traceability (current go-live phase)
Usage Notes
1. Replace DRI role names with actual team member names before distribution.
2. Update Status column as each item is verified (Pending → In Progress → Done).
3. DRI Owner executes; DRI Reviewer validates and signs off.
4. Use Remarks column for evidence links (screenshots, test reports, config screenshots).
5. Review in daily Forge implementation stand-ups; escalate Blocked items immediately.
6. This checklist is specific to Fynd Forge MES at NeoLync.
7. Edge Client = Forge Edge Client EXE